## Sheet1
S.No | Date | Module | Page | Issue Description | Steps | Raised By | Assigned To | Status | Priority | FE/BE | Comments(Dev/QA)
1 | 27Nov | Asset Listing | Bridge Add | Asset Group should not be editable and by default it should display as Bridge | Login - Asset Listing - Bridge - Add Bridge | Priya | Vasanth | Closed |  | FE | Disable working Fine. since user is not going to choose any option whether still it needs to be a dropdown. Priya - Already discussed the same with Shriram , he is ok with even textbox, due to time constraint we have not raise it for control type change , please fix it to textbox if possible
2 | 27Nov | Asset Listing | Bridge Add | Asset Type dropdown shows incorrect list of values | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE | Data need to be modified in background Priya - Please assign to respective person
3 | 27Nov | Asset Listing | Bridge landing | Why do we need with or without images as we are going to show the path of the images only | Login - Asset Listing - Bridge - Download | Priya | kalai | Closed |  | FE | Yet to cross check with team/ This will be worked later as per discussion with aravindhan
4 | 27Nov | Asset Listing | Bridge landing | Detail search - Asset Group should not be editable and by default it should display as Bridge | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  | FE
5 | 27Nov | Asset Listing | Bridge Add | Structure code should not be editable , should be filled based on the Asset Type selected | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed |  | FE | Completed have some query will discuss with prabhu.
6 | 27Nov | Asset Listing | Bridge landing | Asset Type dropdown shows incorrect list of values | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
7 | 27Nov | Asset Listing | Bridge landing | Grid should have column RMU Abbreviation | Login - Asset Listing - Bridge | Priya | Vasanth | Closed |  | FE | Discussed with prabhu to update the model vasanth will be working on htis 13Dec - RMU Abbreviation column header needs to be finalised and change accordingly
8 | 27Nov | Asset Listing | Bridge Add | Page should have column RMU Abbreviation | Login - Asset Listing - Bridge - Add Bridge | Priya | Vasanth | Closed |  | FE
9 | 27Nov | Asset Listing | Bridge Add | Asset Id should generate with RMU abrrevation instead RMU Name | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
10 | 27Nov | Asset Listing | Bridge Add | Location chainage is missing in Asset Id | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
11 | 27Nov | Asset Listing | Bridge Edit | Reference Number is missing in Edit | Login - Asset Listing - Bridge - Edit | Priya |  | Closed
12 | 27Nov | Asset Listing | Bridge landing | Location CH in the grid shows only the KM value it should be the concatenated value of both KM and M | Login - Asset Listing - Bridge | Priya | kalai | Closed
13 | 27Nov | Asset Listing | Bridge Edit | Road Feature Id should not be editable in Edit mode | Login - Asset Listing - Bridge - Edit | Priya | kalai | Closed
14 | 27Nov | Asset Listing | Bridge Add | In Sections: Primary Member & Secondary Member- For Dropdown value "Others(To be fill up) need to change to "Others" Textbox should be enabled for "Others" value choosen | Login - Asset Listing - Bridge - Add Bridge | Roopak | Prabhu | Closed
15 | 27Nov | Asset Listing | Bridge Edit | RMU shows RMU Abbreviation value | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed |  |  | handled already
16 | 27Nov | Asset Listing | Bridge Edit | Property section should be non editable | Login - Asset Listing - Bridge - Edit | Priya | kalai | Closed
17 | 27Nov | Asset Listing | Bridge landing | Grid should have column No | Login - Asset Listing - Bridge | Roopak | kalai | Closed |  |  | Not Required as per Priya's confirmation 11Dec - Priya - Confirmed by Ariff and Senthil in a demo
18 | 27Nov | Asset Listing | Bridge Add | Next to Asset Type KM and M textbox should be placed , followed by Bound dropdown should be placed | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
19 | 27Nov | Asset Listing | Bridge landing | In Grid column headers are in incorrect order after "Location CH" header name | Login - Asset Listing - Bridge | Roopak | kalai | Closed |  |  | Need to Cross check with Shriram
20 | 27Nov | Asset Listing | Bridge Add | parapet,Railing should be Parapet, Railing | Login - Asset Listing - Bridge - Add Bridge | Roopak | kalai | Closed
21 | 27Nov | Asset Listing | Bridge Add | Walk Way should be Walkway(m) | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
22 | 27Nov | Asset Listing | Bridge Add | Super Structure should be Superstructure | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
23 | 27Nov | Asset Listing | Bridge Add | After "," space should be included in the fields for Primary Member and Secondary Member sections | Login - Asset Listing - Bridge - Add Bridge | Roopak | kalai | Closed
24 | 27Nov | Asset Listing | Bridge Add | Bearing,Bearing Seats,Bearing Diaphgram spelling mistake should be Diaphragm | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
25 | 27Nov | Asset Listing | Bridge Add | Drain Water Down Pipe,Drinage spelling mistake should be Drainage | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
26 | 27Nov | Asset Listing | Bridge Add | Expansion joint should be Expansion Joint | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
27 | 27Nov | Asset Listing | Bridge Add | Slope protection,Retaining Wall change p to caps in protection | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
28 | 27Nov | Asset Listing | Bridge Add | Super Structure shows a value S which is wrong it should be Suspension | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
29 | 27Nov | Asset Listing | Bridge Add | Parapet type - New Jersey with Railing should be New Jersey Parapet with Railing | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
30 | 27Nov | Asset Listing | Bridge Add | Bearing Type - Elastometric should be Elastomeric | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
31 | 27Nov | Asset Listing | Bridge Add | Expansion Type - Elastometric should be Elastomeric | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
32 | 27Nov | Asset Listing | Bridge Add | Deck Type - Pre-Stresed should be Pre-Stressed | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
33 | 27Nov | Asset Listing | Bridge Add | Bearing,Bearing Seats,Bearing Diaphragm dropdown remove the value Timber | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
34 | 27Nov | Asset Listing | Bridge Add | Signboard,Utilities change the dropdown value Steel to Steel/Metal/Aluminium | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
35 | 27Nov | Asset Listing | Bridge Add | Slope Protections,Retaining Wall include a dropdown value Natural | Login - Asset Listing - Bridge - Add Bridge | Priya | Prabhu | Closed |  | BE
36 | 27Nov | Asset Listing | Asset Listing | Click ME change to Click Me |  | Priya | kalai | Closed
37 | 27Nov | Asset Listing | Asset Listing | Navigation thru Breadcrumb not working |  | Priya | Vasanth | Closed |  |  | Need to discuss 12Dec Priya - Better we can just have this bread crumb non editable , discussed with Kalai
38 | 28Nov | Asset Listing | Bridge Download | Name of the file which getting download | Login - Asset Listing - Bridge- Download | Priya | kalai | Closed |  |  | Need to confirm the expectation with BA
39 | 28Nov | Asset Listing | Bridge Download | Columns headers in dowloaded file order is incorrect | Login - Asset Listing - Bridge- Download | Roopak | Manikandan | Closed |  | Later | Cross checked working fine if further devleopment is going to take place there will hanlde this 22Dec - Priya - Tracked in Asset-Import/Download sheet - S.No 24
40 | 28Nov | Asset Listing | Bridge | Help icon missing next to search icon | Login - Asset Listing - Bridge | Priya | Designer | Closed | Medium | Later | Raised as the clarification to BA once got updaate will start working in this 23Dec - Priya - S.No 112 raised as common bug
41 | 28Nov | Asset Listing | Bridge | Detail Search - Serach By CH From and CH To not working | Login - Asset Listing - Bridge - Detail Search | Priya | Pravin/kalai | Closed |  |  | As per the discussion with BA,Aravindhan and PRiya value will be searched from location 1km 2M to 5Km and M | Cross check with Prabhu Location ch has been separated as loc ch from- km and meter and loc ch to - km m, Since there is no separate field in add for ch from and to there is no data for corresponding field, hence returns null. Currently it checks CH from, TO(Km and M). Need more clarification from Shiram and Prabhu
42 | 28Nov | Asset Listing | Bridge landing | Detail search - Asset Type list incorrect data | Login - Asset Listing - Bridge - Detail Search | Priya |  | Closed
43 | 28Nov | Asset Listing | Bridge landing | Detail search - RMU dropdown shows duplicate value | Login - Asset Listing - Bridge - Detail Search | Priya | prabhu | Closed
44 | 28Nov | Asset Listing | Bridge landing | Detail search - Need to rearrange the search control | Login - Asset Listing - Bridge - Detail Search | Priya | Nachiappan | Closed | Low |  | Dec 16 As per priya's Suggestion we have reorder the controls in detail search move loction control after bound, Confirmed with BA
45 | 28Nov | Asset Listing | All Asset | Detail search by (individual) - Section Code (dropdown) , Section Name(autofill), Road Name(autofill based on Road Code) | Login - Asset Listing - Bridge - Detail Search | Priya | Pravin/kalai | Closed |  |  | Need to discuss with priya
46 | 28Nov | Asset Listing | Bridge landing | Detail search - Road Code - dropdown values are missing | Login - Asset Listing - Bridge - Detail Search | Priya | Kalai | Closed
47 | 28Nov | Asset Listing | Bridge landing | Detail search - Dropdown dependency is missing | Login - Asset Listing - Bridge - Detail Search | Priya | Pravin/kalai | Closed |  |  | As per discussion with Aravindhan and priya Forward dependency will be WF Back ward will work some case based on priority backward data will refresh. So this can be handle later if needed 12Dec - Priya - Better to have clear button also , feel little confusing , lets wait for customer feedback
48 | 28Nov | Asset Listing | Bridge | Detail Search - Serach By Section Name (BATU NIAH) not working | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  |  | Section Name changed to autofill
49 | 28Nov | Asset Listing | Bridge | Detail Search - Serach By Section Code(5) not working | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  |  | BE data is mis matched updated the record based on the road master table in ddlookup for section code 5
50 | 28Nov | Asset Listing | Bridge | Asset Id should generate with Bound code instead Bound Name | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
51 | 28Nov | Asset Listing | Bridge | Smart search brings irrelevant data , type 3 in smart search, system populates this Id BR/CS/MIRI/1/Q445/0.0/LR , which does not contain 3 in any of the column in the grid | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed
52 | 28Nov | Asset Listing | Bridge | In Downloaded file, column: "No" is missing | Login - Asset Listing - Bridge- Download | Roopak | kalai | Closed |  |  | Discussed with BA as per Sagar confirmation SNo is not going to be added | Whether S.No need to be included in both Grid and Asset mass download. whether it it going to be continuous No/any Pk No. - Sagar - Not needed | Sagar - Not needed
53 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Road Name (ex Davidson Road) | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  |  | Section Name changed to autofill
54 | 28Nov | Asset Listing | Bridge | In Downloaded file, "Location CH" column is displaying twice(remove the extra column) | Login - Asset Listing - Bridge- Download | Roopak | kalai | Closed
55 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Location CH(ex 10) | Login - Asset Listing - Bridge - Detail Search | Priya | ;poy | Closed
56 | 28Nov | Asset Listing | Bridge | In Downloaded file, "Location CH" data is missing | Login - Asset Listing - Bridge- Download | Roopak | kalai | Closed
57 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Bridge Name(ex New Bridge) | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  |  | Already fixed
58 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Bridge Length(ex 15.9) | Login - Asset Listing - Bridge - Detail Search | Priya | Pravin | Closed
59 | 28Nov | Asset Listing | Bridge | Asset Id should generate with Asset Type Code (Structure code) instead Asset Type Name | Login - Asset Listing - Bridge - Add Bridge | Priya | kalai | Closed
60 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Type of Bridge (ex Long Bridge > 100m) | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed |  |  | WF Record with the mentioned id is inactive
61 | 28Nov | Asset Listing | Bridge | Smart search not populating data based on Bridge Id (ex BR/Long Bridge > 100m/BTN/5/Q2007/0.0/Left Right) | Login - Asset Listing - Bridge - Detail Search | Priya | kalai/Pravin | Closed |  |  | 11Dec - Priya- Please try to search this id - BR/CC/MRI/1/Q288/5+620/LR
62 | 28Nov | Asset Listing | Bridge | No of records in the Showing Results section under grid shows 7 of 8 but there are only 7 records so it is expected to show 7 of 7 | Login - Asset Listing - Bridge - Detail Search | Priya | kalai | Closed
63 | 28Nov | Asset Listing | Bridge | Detail Search Combination (Asset Group, Asset Type, RMU,Bound)) - not populating the expected data on search (Bridge,Long Bridge > 100m, BATU NIAH,Left Right) | Login - Asset Listing - Bridge - Detail Search | Priya | kalai/pravin | Closed
64 | 28Nov | Asset Listing | Bridge | Bound column in the grid should be placed next to Location CH | Login - Asset Listing - Bridge | Priya | kalai | Closed |  | Later | Grid column rearranged will be hanled later
65 | 28Nov | Asset Listing | Bridge | In Kerb,Sidewalks,Approaches,Approaches Slab, ReinforcedConcrete should be Reinforced Concrete(need space) | Login - Asset Listing - Bridge - Add Bridge | Roopak | Prabhu | Closed
66 | 28Nov | Asset Listing | Bridge | In Slope protection,Retaining Wall, Gabinor need to be changed to Gabion | Login - Asset Listing - Bridge - Add Bridge | Roopak | Prabhu | Closed
67 | 28Nov | Asset Listing | Bridge | In Parameter and Property section, Reference No, Km, m, Lane Width, Span Length, Median(m),Walkway(m), No of Span, No of Lane, No of Expansion Joint and Spacing of Expansion Joint field decimal values not displayed on edit(ex: 3.5) | Login - Asset Listing - Bridge - Add Bridge | Roopak | kalai | Closed |  |  | Fixed span and lane are int field it is just the count
68 | 28Nov | Asset Listing | Culvert | RMU Abbrevation column is missing in grid | Login - Asset Listing - Culvert | Shalini | Vasanth | Closed |  | FE
69 | 28Nov | Asset Listing | Culvert | Culvert Width,Culvert Height,Length,Asset Type,Culvert Material and Barrel Number - Order is mismatching in grid | Login - Asset Listing - Culvert | Shalini | Vasanth | Closed |  | Need to discuss
70 | 28Nov | Asset Listing | Culvert | Culvert Id should generate with Asset Group CV(instead of BR) | Login - Asset Listing - Culvert | Shalini | Vasanth | Closed |  | FE
71 | 28Nov | Asset Listing | Culvert | Intel Structure field change to "Inlet Structure | Login - Asset Listing - Add Culvert | Roopak | kalai | Closed
72 | 28Nov | Asset Listing | Culvert | No dropdown values available in Culvert Material, Precast/In-situ, Inlet Structure and Outlet Structure | Login - Asset Listing - Add Culvert | Roopak | Vasanth | Closed |  | FE
73 | 28Nov | Asset Listing | Culvert Download | Columns headers in dowloaded file order is incorrect | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed
74 | 28Nov | Asset Listing | Culvert Download | Design Flow,District,Division Code- need to remove this column | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed |  | FE
75 | 28Nov | Asset Listing | Culvert Download | 'RMU Code' column name should be change as RMU | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed |  | FE
76 | 28Nov | Asset Listing | Culvert Download | Instead of 'Find Road Level' need to change it as Finished Road Level | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed |  | FE
77 | 28Nov | Asset Listing | Culvert Download | No,Road Feature id,Location CH columns are missing | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed |  | FE
78 | 28Nov | Asset Listing | Culvert Download | Diameter,Width,Height,Material,Length,Skew-Change the column name (ex.Culvert Width) | Login - Asset Listing - Culvert- Download | Shalini | Vasanth | Closed |  | FE
79 | 28Nov | Asset Listing | Culvert | ID should generate with Asset Group CV(instead of BR) | Login - Asset Listing - Add Culvert | Roopak | Vasanth | Closed |  | FE
80 | 28Nov | Asset Listing | Culvert Download | Catch Area,Precast-Column name is incorrect | Login - Asset Listing - Culvert- Download | Shalini |  | Closed
81 | 28Nov | Asset Listing | Culvert | Reference No, Km, m, Finished Road Level, Catchment Area, Culvert Skew, Design Flow, Inlet Level and Outlet Level field decimal values not displayed on edit(ex: 3.5) | Login - Asset Listing - Add Culvert | Roopak | Vasanth | Closed |  | FE
82 | 28Nov | Asset Listing | Culvert Add and Landing page | Requirement Change - Asset Type dropdown should have the below values Pipe Box Arch Bridge Metal Others |  | Priya | Prabhu | Closed |  | Backend added the asset type for Culvert. (select * from RM_DD_LOOKUP where ddl_type = 'Asset Type' and DDL_Type_code = 'CV') Frontend need to change the dropdown values accordingly. Priya - Prabhu please revert the changes with old values of culvert asset type , as for this values client wants to have a seperate field called 'Culvert Type' | 11 Dec - Priya - This is not an issue , should maintain the old values
83 | 28Nov | Asset Listing | Bridge | In Expansion Joint and Slope Protection, Retaining Wall dropdown value, Rubber/RubberPitching should be "Rubber/Rubber Pitching" | Login - Asset Listing - Add Bridge | Roopak | Prabhu | Closed
84 | 28Nov | Asset Listing | Bridge | In Screen size set to 90, Drain Water Down Pipe,Drainage field label position is incorrect | Login - Asset Listing - Add Bridge | Roopak | designer | Closed | Low | need to discussed
85 | 28Nov | Asset Listing | Add Bridge | Additional documents tab missing | Login - Asset Listing - Add Bridge | Priya | kalai | Closed |  |  | Confirmed with Sagar instead of separate tab by choosing the others in the list other doc could be added. Dec 14 Also raised in Clarification sheet once confirmed will move this to fixed
86 | 29Nov | Asset Listing | Bridge | Unable to view the dropdown values completely in all the section |  | Priya | designer | Closed |  | need to discussed
87 | 29Nov | Asset Listing | Bridge | Import Sheet - Unable to import more than one record |  | Priya | kalai | Closed |  |  | WF
88 | 29Nov | Asset Listing | Bridge | After import , for other records in the grids images are not getting load immediately or unable to upload images (performance issue) |  | Priya | kalai | Closed | Low | Later | As the requirement is about to change import is going to be handled later
89 | 29Nov | Asset Listing | Bridge | Image Upload - On clicking upload , system navigates to landing page and it behaves like submit |  | Priya | kalai | Closed |  |  | WF
90 | 29Nov | Asset Listing | Bridge | Images Upload - Adding more than four images , unable to access upload button |  | Priya | kalai | Closed |  |  | WF
91 | 29Nov | Asset Listing | Bridge | Images Upload - S.No and delete icon is missing |  | Priya |  | Closed
92 | 29Nov | Asset Listing | Bridge | Images download - Unable to connect to the download path |  | Priya | kalai | Closed
93 | 29Nov | Asset Listing | Bridge / Image Upload | Generally on clicking outside the modals system navigates to previous page |  | Priya | Nisha | Closed
94 | 29Nov | Asset Listing | Bridge | UI - Adding multiple values in one dropdown and single value in other dropdown , control are getting rearranged (ex Abutment and Pier type) |  | Priya | designer | Closed | High | need to discussed
95 | 29Nov | Asset Listing | Bridge | On Confirming a record (add/edit,delete) system navigates to the landing page and the UI of the landing page looks different |  | Priya | kalai | Closed |  |  | WF
96 | 8Dec | Asset Listing | Bridge | Cannot able to view the data completely in Asset ID field | Login - Asset Listing - Bridge - Add Bridge | Roopak | designer | Closed
97 | 8Dec | Asset Listing | Bridge | Add image button is missing in Add page | Login - Asset Listing - Bridge - Add Bridge | shalini | kalai | Closed |  |  | 14th Dec: Cross checked the screnerio with BA that only after saving the page1 data add image button will be displayed in page2(photo section)
98 | 8Dec | Asset Listing | Culvert | In Grid need to change Culvert type into Asset Type | Login - Asset Listing -Culvert Landing page | shalini | Nisha | Closed
99 | 8Dec | Asset Listing | Culvert | Photo Type dropdown values are empty | Login - Asset Listing - Culvet - Add Culvert | shalini | Nisha-tested only | Closed
100 | 8Dec | Asset Listing | Culvert | Need to change RMU Code as RMU Name | Login - Asset Listing -Culvert Landing page | shalini | Nisha-tested only | Closed
101 | 8Dec | Asset Listing | Bridge | Location Ch' label name should change to 'Location CH' | Login - Asset Listing - Bridge - Add Bridge | Roopak |  | Closed
102 | 8Dec | Asset Listing | Bridge | In 'Image List' section, showing same image types, if all phototypes are uploaded in photo tab | Login - Asset Listing - Bridge -Click Me->View Photo | Roopak | kalai | Closed | High |  | Need Clarification as of now tested with the all image type it is working fine 13Dec - Click on upload after selecting images for all types
103 | 8Dec | Asset Listing | Bridge | In 'Image View' section, showing same image type for all images(different photo type) | Login - Asset Listing - Bridge -Click Me->View Photo | Roopak | kalai | Closed | High |  | Need Clarification
104 | 8Dec | Asset Listing | Bridge | Deleted images' in 'Image List' is showing incorrect order in 'Image View'(ex: 2,3,4,5,6) | Login - Asset Listing - Bridge -Click Me->Edit(Photo) | Roopak | kalai | Closed |  |  | no under image represent the image uploaded no not the S.No. Ex. BRCSMIRI1Q422200LR_Carriageways_001 - 001 is the num under image in view
105 | 8Dec | Asset Listing | Bridge | Showing Image Unavailable in 'Image View' section | Login - Asset Listing - Bridge -Click Me->Edit(Photo)/View Photo | Roopak | kalai | Closed |  |  | Image uploaded locally not committed hence due to path miss match it show unavailable.
106 | 8Dec | Asset Listing | Bridge | In parapet,Railing dropdown value 'timber' should change to 'Timber | Login - Asset Listing - Bridge - Add Bridge | Roopak | Nisha/Prabhu | Closed
107 | 8Dec | Asset Listing | Bridge | In Grid 'RMU Code' column name should change to RMU Name | Login - Asset Listing -Bridge Landing page | Roopak | Nisha-tested only | Closed
108 | 8Dec | Asset Listing | Bridge | In 'Image List' section, allowing images to delete | Login - Asset Listing - Bridge -Click Me->View Photo | Roopak | kalai | Closed
109 | 9Dec | Asset Listing | Bridge | Click ME change to Click Me | Login - Asset Listing - Bridge -Click Me->View Photo | Roopak |  | Closed
110 | 10Dec | Asset Listing | Culvert | Change Section code as dropdown instead of textbox in Detail Search | Login - Asset Listing - Culvert | Shalini | kalai | Closed
111 | 10Dec | Asset Listing | Culvert | Detail search - Road Code - dropdown values are missing | Login - Asset Listing - Culvert | Shalini | Prabhu | Closed
112 | 10Dec | Asset Listing | All Asset | Help Icon is missing | Login - Asset Listing | Priya | designer | Open | Low | Later | Requested for the template to develope
113 | 10Dec | Asset Listing | Culvert | Cannot able to view all the values in Asset Type and Bound dropdown | Login - Asset Listing - Culvert -Add | Shalini | designer | Closed
114 | 10Dec | Asset Listing | All Asset | District Textox is missing in the property section | Login - Asset Listing | Shalini | Nisha | Closed
115 | 10Dec | Asset Listing | Culvert | Change Location ch to Location CH(Caps H) in Culvert property page | Login - Asset Listing - Culvert -Add | Shalini |  | Closed
116 | 10Dec | Asset Listing | All Asset | Others - should have textbox to enter addtional value | Login - Asset Listing - Culvert -Add | Shalini | Nisha/Nachiappan | Closed |  | Wants to check
117 | 10Dec | Asset Listing | All Asset | On clicking outside the modal (Bridge Property) , modal is getting closed | Login - Asset Listing - Culvert -Add | Priya | Nisha/Nachiappan | Closed |  |  | Added Other field for Culvert
118 | 10Dec | Asset Listing | All Asset | Freeze the property section until user select the Road Feature Id | Login - Asset Listing | Priya | kalai | Closed
119 | 10Dec | Asset Listing | All Asset | Structure code should list the code not the value | Login - Asset Listing | Priya | vasanth | Closed |  |  | 13Dec - Priya - It is autofill and filling the structure code as expected
120 | 10Dec | Asset Listing | All Asset | Upload 2 images for a type , delete the first image , still the image number remains as 2 | Login - Asset Listing | Priya | kalai | Closed |  |  | As per senthil requirement we are not showing the sno of grid under image. instead showing the Sno of the BE which is appended in image name 13Dec - Priya - Completely agree , but I dont think so , it should be handled in this way , as it will mislead user , the no is is to identify the number of images . Pease discuss if you need more clarity Dec 14 As per discussion with Sagar(BA) - We are going to show the File name generated with our system will be showed under the image in preview section. Priya Agreed with Name/SNO
121 | 10Dec | Asset Listing | All Asset | System expects manual refersh for the grid to popoulate the data even appling the filter , instead after confirming a record system should close the model , refresh the grid and populate the data in the grid | Login - Asset Listing | Priya | kalai | Closed |  | WF | Discussed with BA after saving photo page need to be redirected. Page has been redirected to photo Dec 14 As per confirmation of Sagar on 11.12.2020 once after saving modal will not be closed will be redirected to photo section. Modal only be closed manually
122 | 10Dec | Asset Listing | All Asset | Photo Type-Other-It will upload the default image for other | Login - Asset Listing - Add | Shalini | Nisha | Closed |  |  | 13Dec - Priya - Right now it is implemented with the default image
123 | 10Dec | Asset Listing | All Asset | GPS Easting and Northing increase the decimal places to max | Login - Asset Listing - Add | Priya | Nachiappan | Closed |  | As per dis with Priya we have increased digits up to 5. In future we will restric the user in typing more than 5 decimal digit | 13Dec : Still receiving the validation msg that only digits on submitting Dec 16 As per dis with Priya we have increased digits up to 5. In future we will restric the user in typing more than 5 decimal digit
124 | 10Dec | Asset Listing | All Asset | Instead of RMU Code need to change as RMU Abbrevation | Login - Asset Listing - Add | Shalini | kalai | Closed
125 | 10Dec | Asset Listing | Culvert | Change Culvert Type to Asset Type in the grid | Login - Asset Listing - Add | Priya |  | Closed
126 | 10Dec | Asset Listing | Drain | Change Drain Type to Asset Type in the grid | Login - Asset Listing - Add | Priya |  | Closed
127 | 10Dec | Asset Listing | All Asset | Duplicate records should not be allowed | Login - Asset Listing | Priya | kalai | Closed | High | Dec 16 As per discussion with Sagar when User tries to add records with already exist asset id, Toaster will be thrown that duplicate exist and user can't add further | 14Dec-Shalini-New Record will update with the existing record(and the existing values are get shown with the new one eg:Length-1,width-2) 15Dec - BA has a different perspective , Sagar please provide your suggestion Sagar - If we can identify the record is duplicate while adding itself, then we can show a message to user before they clicking confirm button Dec 15 Spoke to Sagar, Once after he got clarification from shriram we will proceed further in this
128 |  | Asset Listing | Drain |  |  |  |  | Closed
129 | 10Dec | Asset Listing | All Asset | Cant able to view the photo using downloaded file path | Login - Asset Listing - Download | Shalini | kalai | Closed
130 | 10Dec | Asset Listing | All Asset | Other column is missing in Downloaded sheet if choosing structure code -Other | Login - Asset Listing - Download | Shalini |  | Open | High
131 | 10Dec | Asset Listing | All Asset | In Grid, RMU column-should be in Miri and RMU Abbrevation column -should be in MRI | Login - Asset Listing | Shalini | kalai | Closed
132 | 2021-12-10 | Asset Listing | Carriageway | Menu name need to correct Currently Menu name is Carriage Way so we need to update Carriageway |  | Shalini | Vasanth | Closed
133 | 2021-12-10 | Asset Listing | Carriageway | Need to update the Column name From CH changed to CH From | Login - Asset Listing - Carriageway Issue : Grid column rename | Shalini | Vasanth | Closed
134 | 2021-12-10 | Asset Listing | Carriageway | Need to update the Column name To CH changed to CH To | Login - Asset Listing - Carriageway Issue : Grid column rename | Shalini | Vasanth | Closed
135 | 2021-12-10 | Asset Listing | All Asset | Need to update the Column name carriageway Type changed to Asset Type Note : Its an common issue we need to show Asset Type in grid | Login - Asset Listing - Carriageway Issue : Grid column rename | Shalini |  | Closed
136 | 2021-12-10 | Asset Listing | All Asset | Cursor and focus should be showed in first filed | Login - Asset Listing | Shalini | Designer | Open | Low
137 | 2021-12-10 | Asset Listing | Carriageway | Cursor focus are not showed in below iteams 1) Search icons 2) Details search icons | Login - Asset Listing - Carriageway | Shalini | Nisha | Closed |  | 18Dec - Priya - Not working link
138 | 2021-12-10 | Asset Listing | All Asset | After Reaching Pagination. I cant see the cursor movement. so after pagination cursor should be moved in search field | Login - Asset Listing | Shalini | Designer | Open | Low
139 | 2021-12-10 | Asset Listing | Carriageway | In carriageway property screen Shows as Two pannel 1) Property 2) Parameter Issue : Currently both pannel are showed as property | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | kalai | Closed
140 | 2021-12-10 | Asset Listing | Carriageway | CH From showed only one filed | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | Vasanth | Closed |  |  | Ch from only field mentioned in write frame 12Dec-Priya - As per the change in Location Ch the same needs to be implemented to CH From and To as well (needs to be splited in to two boxes seperated by + , we have already discussed with BA - Please confirm with BA and fix it acordingly
141 | 2021-12-10 | Asset Listing | Carriageway | CH To showed only one filed | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | Vasanth | Closed |  |  | Ch from only field mentioned in write frame 12Dec-Priya - As per the change in Location Ch the same needs to be implemented to CH From and To as well (needs to be splited in to two boxes seperated by + , we have already discussed with BA - Please confirm with BA and fix it acordingly
142 | 2021-12-10 | Asset Listing | Carriageway | while user enter the Location CH field at the time screen is automatically loading we need to restrict the loading | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | kalai | Closed |  |  | Id will be generated based on location hence loading is needed 12Dec - Priya - Need to discuss
143 | 2021-12-10 | Asset Listing | All Asset | Validation need to refresh for below scenario Step 1 : Navigate the Add Carriageway property Step 2 : without fill the some required field > Click Confirm Note : through Some error Step 3 : now fill the all required field > click Confirm Issue : saved successfull message appeared but still showed the validation messages near cancel Once saved means old message should be refreshed | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | designer | Open | High | Pending
144 | 2021-12-10 | Asset Listing | Carriageway | Browse files not able to delete We need to give the delete icon for browse filed | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini |  | Closed | Medium | Pending
145 | 2021-12-10 | Asset Listing | Carriageway | While user upload the file > Loading bar should be appeared | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | Vasanth | Closed
146 | 2021-12-10 | Asset Listing | Carriageway | Lane no filed not showed in Carriageway property screen | Login - Asset Listing - Carriageway - click Add Carriageway | Shalini | kalai | Closed |  |  | 11Dec - Priya - Should be a dropdown as per the req Prabhu need to update in table once done, we will update accordingly in FE. 14Dec-Shalini - As per BA Confirmation>Lane No dropdown should have values(L1 and L2)-Closed
147 | 2021-12-10 | Asset Listing | Carriageway | We need to swap Column name RMU Abb. and RMU Name | Login - Asset Listing - Carriageway | Shalini | Vasanth | Closed
148 | 2021-12-10 | Asset Listing | All | User should be receive a validation msg "Unsaved changes will be lost. Are you sure you want to cancel? " This error is reduce the data lose | Login - Asset Listing - Carriageway - click edit Carriageway - enter the filed - click cancel This should appear while user click Cancel in Add and update screen | Shalini | Nisha | Closed
149 | 2021-12-10 | Asset Listing | Carriageway | In Download Excel Docuement GPS Easting and GPS Northing field are not populated | Login - Asset Listing - Carriageway - Click asset Import | Shalini | Vasanth | Closed
150 | 2021-12-10 | Asset Listing | Carriageway | While update the record cord GPS Easting and GPS Northing fileds are not populated | Login - Asset Listing - Carriageway - Update button | Shalini | Vasanth | Closed
151 | 2021-12-10 | Asset Listing | Carriageway | In Download Excel Docuement District fileds are not showed in the excel | Login - Asset Listing - Carriageway - Asset Import | Shalini | kalai | Closed |  |  | District fields was not given in the download template Dec 23 District column was not given in the excel Asset091020 DEC 24 QA: while i testing download functionality in carriage way screen> at the time Object error is passed As per discuss with Kathiravan after clear the cookies. its working fine
152 | 2021-12-10 | Asset Listing | All Asset | Reference No should be varchar not only nunber |  | Priya | Vasanth | Closed | High |  | Prabhu need to update in table once done, we will update accordingly in FE. 13Dec : Priya - Reopend and assigned to Vasanth , as the FE part is remaining Dec 14 Waiting for Prabhu to modify the col as varchar. Once done will proceed in FE
153 | 2021-12-11 | Asset Listing | Drain | Road code in search is not listing all the road code values | Login - Asset Listing - Drain - Advance search | Priya | kalai | Closed
154 | [7 empty] | Closed
155 | 2021-12-11 | All Asset |  | Reference No is not required field , exclude from mandatory list , also in the validation msg Asset Title is require , which field it is representing if Id no need to include in the msg as it is auto generate | Login - Asset Listing | Priya | kalai | Closed
156 | 11Dec | All Asset | All Asset | Click Me-View -Able to delete photo in view mode | Login - Asset Listing - Ditches | Shalini | Vasanth | Closed
157 | 11Dec | Asset Listing | Ditches | Click Me-View Photo -Able to delete photo in view mode | Login - Asset Listing - Ditches | Shalini | Vasanth | Closed
158 | 11Dec | All Asset | All Asset | Upload more than 7 photos -then the remaining photo will move out of the screen | Login - Asset Listing | Shalini | kalai | Closed | High | designer
159 | 11Dec | All Asset | All Asset | Tried by adding photo and a document at once, but instead of the document the photo itself added twice | Login - Asset Listing - Drain - Add drain - photo - Add image | Priya | kalai | Closed | High
160 | 11Dec | All Asset | Drain | Structure code is autofilled with Asset type name instead of code | Login - Asset Listing - Drain - Add drain | Priya | Vasanth | Closed
161 | 11Dec | All Asset |  | < Id > is missing in sucessful message | Login - Asset Listing - Drain - Add drain - Confirm | Priya | kalai | Closed
162 | 11Dec | All Asset | Drain | Modal is not closing after clicking Confirm also grid is not loading the newly added data until we do manual refresh | Login - Asset Listing - Drain - Add drain - Confirm | Priya |  | Closed |  |  | Discussed with BA after saving photo page need to be redirected. Page has been redirected to photo Dec 14 As per confirmation of Sagar on 11.12.2020 once after saving modal will not be closed will be redirected to photo section. Modal only be closed manually
163 | 11Dec | All Asset | Drain | Didn't show up any validation msg | Login - Asset Listing - Drain - Add drain - Cancel | Priya | Vasanth | Closed
164 | 11Dec | All Asset | Edge line marking | Page title and breadcrumb is missing | Login - Asset Listing - Edge line marking | Priya |  | Closed
165 | 11Dec | All Asset | Edge line marking | Edge Line Marking add model should load by setting Edge line marking as default value in the Asset Group dropdown" | Login - Asset Listing - Edge line marking | Priya |  | Closed
166 | 11Dec | All Asset | Edge line marking | System not populating the existing records by default in the gird while landing on Edge line marking screen | Login - Asset Listing - Edge line marking | Priya |  | Closed
167 | 11Dec | All Asset | Edge line marking | Asset type is not listing all the types in advance search | Login - Asset Listing - Edge line marking | Priya |  | Closed
168 | 11Dec | All Asset |  | Can we enable district and reference number in edit as these field are mandatory for asset id generation |  | Priya | Vasanth | Closed |  |  | Need to Confirm with BA
169 | 2021-12-11 | Asset Listing | Carriageway | Navigation and button name is automatically changed Carriageway only should be appeared Issue araised by window | Login - Asset Listing - Carriageway | Shalini |  | Closed
170 | 11Dec | All Asset | All Asset | Click Me-View-Cancel button is missing in View modal | Login - Asset Listing | Shalini | kalai | Closed
171 | 2021-12-11 | All Asset | Carriageway | User try to Delete one record or uploaded file at the time user click ok for two times Once user click Delete button > validation is appeared > user click ok means Deleted successfully message should be showed in toaster messages | Login - Asset Listing - Carriageway | Shalini | kalai | Closed | Medium |  | Toaster is added need what exactly required since it is reopened Dec 15 Cross checked with Shalini this Issue, When user Delete any Record -> Delete -> Alert Pop up -> clicks(Ok) -> Toaster(Successfully Deleted) will be shown
172 | 2021-12-11 | Asset Listing | Carriageway | User search the carriageway ID in search filed but record are not showed in the grid Carriageway ID - CW/Asphalt/MRI/1/Q290/1+222/R | Login - Asset Listing - Carriageway | Shalini | kalai | Closed
173 | 2021-12-11 | Asset Listing | Carriageway | User Search 0.0 means shows some unwanted record | Login - Asset Listing - Carriageway | Shalini |  | Closed
174 | 2021-12-11 | Asset Listing | Carriageway | User search 10 means shows some unwanted record | Login - Asset Listing - Carriageway | Shalini | Pravin | Closed
175 | 2021-12-11 | Asset Listing | Carriageway | In carriageway grid CH From and CH To should be showed KM and M value Its applicable for Details search also | Login - Asset Listing - Carriageway | Shalini | Pravin | Closed
176 | 2021-12-11 | Asset Listing | Ditch | Menu>Asset Listing>Change Ditch(instead of Ditches) | Login - Asset Listing | Shalini |  | Closed
177 | 2021-12-11 | Asset Listing | Ditch | Photo Type>Change Ditch(instead of Ditches) | Login - Asset Listing -Add | Shalini |  | Closed
178 | 2021-12-11 | Asset Listing | Ditch | In detail search>Section name dropdown autofilled values are mismatching(eg;2-Mulu/Bario) | Login - Asset Listing | Shalini |  | Closed
179 | 2021-12-11 | Asset Listing | All Assets | Detail Search Combination (Location Chainage From and To) - not populating the expected data on search | Login - Asset Listing | Shalini | Pravin | Closed | High
180 | 2021-12-11 | Asset Listing | Ditch | Smart search not populating data based on Id (ex.DI/G/MRI/1/Q288/1+100/R) | Login - Asset Listing | Shalini |  | Closed
181 | 2021-12-11 | Asset Listing | Carriageway | Suggestion : we are adding Clear button. its very helpful to remove the button | Login - Asset Listing - Carriageway | Shalini | kalai | closed | Low | Suggestion
182 | 2021-12-11 | Asset Listing | All Asset | Latest Added record should be showed in first record | Login - Asset Listing - Carriageway | Shalini | pravin | Closed
183 | 2021-12-11 | Asset Listing | All Asset | validation message need to change Location Ch KM is required. - we need to change CH Location Ch M is required. - we need to change CH | Login - Asset Listing - Carriageway | Shalini |  | Closed
184 | 2021-12-11 | Asset Listing | Drain | Bound value should display only code as per the requirement except the bound dropdown | Login - Asset Listing - Drain | Priya | Vasanth | Closed
185 | 2021-12-11 | Asset Listing | All Asset | Reference No fileds is not an required | Login - Asset Listing - Carriageway | Shalini |  | Closed
186 | 2021-12-11 | Asset Listing | Road Stud | Page title and breadcrumb is missing | Login - Asset Listing - Road Stud | Shalini |  | Closed
187 | 2021-12-11 | Asset Listing | Road Stud | User click search button without enter any filed Other module record also showed | Login - Asset Listing - Road Stud | Shalini |  | Closed
188 | 2021-12-11 | Asset Listing | Edge line marking | Asset type and RMU abbreviation values are not showing if we go by View mode | Login - Asset Listing - Edge line marking - Action items - View | Priya |  | Closed
189 | 2021-12-11 | Asset Listing | Center line marking | Title & Breadcrumb is missing"Center Line Marking" | Login - Asset Listing - Center line marking | Shalini |  | Closed
190 | 2021-12-11 | Asset Listing | Center line marking | Existing record not shown in the grid | Login - Asset Listing - Center line marking | Shalini |  | Closed
191 | 2021-12-11 | Asset Listing | Center line marking | In Grid-Instead of ID change it as Center Line Marking ID | Login - Asset Listing - Center line marking | Shalini |  | Closed
192 | 2021-12-11 | Asset Listing | Center line marking | In Detail search> Asset Group dropdown-The default value should be Center Line Marking | Login - Asset Listing - Center line marking | Shalini |  | Closed
193 | 2021-12-11 | Asset Listing | Center line marking | Detail Search>In RMU dropdown>Order get changed(Miri should be first and then Batu Niah) | Login - Asset Listing - Center line marking | Shalini | pravin | Closed |  | Wants to discuss with kalai | 13Dec - I feel better to display all the drop down values in alphabetical order
194 | 2021-12-11 | Asset Listing | Center line marking | Instead of Add button-Change it as (Add Center Line Marking) button in landing page | Login - Asset Listing - Center line marking | Shalini |  | Closed
195 | 2021-12-11 | Asset Listing | Center line marking | Add-Asset Group-Center Line Marking should be the default value | Login - Asset Listing - Center line marking | Shalini |  | Closed
196 | 2021-12-11 | Asset Listing | Center line marking | Add> ID>Missing Asset Group and Asset Type(eg:CLM/P) | Login - Asset Listing - Center line marking | Shalini |  | Closed |  |  | Issue already Fixed(Nachiappan)
197 | 2021-12-11 | Asset Listing | Center line marking | Add-Title of the page should be Center line marking property | Login - Asset Listing - Center line marking | Shalini |  | Closed
198 | 2021-12-11 | Asset Listing | All Asset | On entering smart search and click on enter - should populate the data as an alternate of clicking search icon | Login - Asset Listing - Center line marking | Priya | kalai | Closed
199 | 2021-12-11 | Asset Listing | All Asset | Unable to search by Ids | Login - Asset Listing | Priya |  | Closed
200 | 2021-12-11 | Asset Listing | All Asset | Issue in ID generation - follow the steps , system shows asset group in asset type | On Add - Select Road Feature Id and then Bound | Priya | kalai | Closed |  |  | As per discussion if there is any particular not available in the id it will be with the double //
201 | 2021-12-11 | Asset Listing | All Asset | Default value 0 need to removed in numumeric fields | Add Page | Priya | kalai | Closed
202 | 2021-12-11 | Asset Listing | All Asset | Image selected are still on the screen after cancel | Add - Photo - Upload a imgae - Cancel - Go to Photo tab | Priya | Vasanth | Closed
202 | 2021-12-11 | Asset Listing | Road Stud | Shows error msg "Images Unavailable" | Add - Photo - Upload a image | Priya | kalai | Closed | High
203 | 2021-12-11 | Asset Listing | All Asset | Double click upload - photo gets upload twice | Add - Photo - Upload a image | Priya | kalai | Closed
204 | 2021-12-11 | Asset Listing | All Asset | Duplicate records (follow the steps) ( I saw this issue in Road Stud , I feel this will the same for all assets , so raising it as common issue) | Navigate to Add page Enter all the data - Confirm Click on Confirm Navigate Photo tab - Confirm Upload photo - Confirm No we can see four records in the grid | Priya | kalai | Closed
205 | 2021-12-11 | Asset Listing | Road Stud (as well as applicable assets) | CH From and CH To - in the grid concatenate (KM+M) and display |  | Priya | Vasanth | Closed |  |  | 11Dec - Priya - Issue no 175 explains the same for Carriageway, may be common fix
206 | 2021-12-11 | Asset Listing | Road Stud (as well as applicable assets) | Detail Search - Section Code - Batu Niah , section name should populate as Batu Niah |  | Priya | Prabhu | Closed |  |  | 11Dec - Priya - Issue no 175 explains the same for Carriageway, may be common fix
207 | 2021-12-11 | Asset Listing | All Asset | Better to show the document name instead 1, 2 etc when we upload file in others category |  | Priya | kalai | Closed
208 | 2021-12-11 | Asset Listing | All Asset | Section Name and Road Name can be autofill and non editable (always ) in the detail search |  | Priya |  | Closed
209 | 2021-12-11 | Asset Listing | All Asset | Smart search by road name not happening (note record is not in inactive state) Asset - Road Stud Test Data - TG. KIDURONG/KUALA SUAI/KUALA NIAH/KUALA SIBUTI/BAKAM ROAD (KM178+130 TO KM174+570) | TG. KIDURONG/KUALA SUAI/KUALA NIAH/KUALA SIBUTI/BAKAM ROAD (KM178+130 TO KM174+570) | Priya | Pravin | Closed |  |  | 11Dec - Priya - I think something issue when we have special characters as we are not able to perform search by Asset Id also which has seperator like / 12 Dec - RS/r/MRI/1/Q2007-2d (A)/1+500/LR , this is the record ID Pravin | Cross checked in BE this record is available in BRidge and ELM and active too. But not available in road studs
210 | 2021-12-11 | Asset Listing | Edge line marking | Rename column in the grid Edge Line Marking Width to Width and Edge Line Marking Length to Length |  | Priya | kalai | Closed |  | pending
211 | 2021-12-11 | Asset Listing | All Asset | Edge Line Marking , Center Line Marking , In view on clicking document attached - shows Page not working (apart from PDF) |  | Priya | Nisha | Closed | High |  | If the uploaded file not available will be redirected to default page i.e doc is unavailable | Working fine need to know the exact steps to reproduce
212 | 2021-12-12 | Asset Listing | All Asset | On unselecting asset type or bound , the whole id itself getting vanished - on unselecting system should just remove the repective section of data instead removing the whole id |  | Priya | kalai | Closed |  |  | clarification needed
213 | 2021-12-12 | Asset Listing | All Asset | Change the font style and size of the data inside the dropdown in to same as others |  | Priya | designer | Open | High
214 | 2021-12-12 | Asset Listing | All Asset | Deleted Successfully in the toster change Fully to fully |  | Priya |  | Closed
215 | 2021-12-12 | Asset Listing | Centre line marking | Rename column in the grid Centre Line Marking Width to Width and Centre Line Marking Length to Length |  | Priya | kalai | Closed |  | pending
216 | 2021-12-12 | Asset Listing | All Asset | Asset Type (Others) , as per the requirement no need to get additional value thru other textbox |  | Priya | kalai | Closed
217 | 2021-12-12 | Asset Listing | All Asset | Page behind the modal . should not be accessible until close the modal |  | Priya |  | Closed | Medium |  | 13Dec - Open the Add page of an asset , clikc on the page behind add , there is some action happeningin the add page
218 | 12Dec | Asset Listing | Retaining Wall | Rename column in the grid Retaining wall Length to Total Length |  | Shalini | kalai | Closed |  | Grid work
219 | 12Dec | Asset Listing | Signs | Rename Field in the Add >Length to Sign Height and Width to Signs Width |  | Shalini | kalai | Closed |  | Grid work
220 | 12Dec | Asset Listing | Signs | Add>Photo Type-Instead of Signs(Add these photo types) Barriers Gantry Beam Footings Anchor Bolts and Mortar Grout Pads Maintenance Access Static Sign Variable Message Sign(VMSs) |  | Shalini | Prabhu | Closed
221 | 2021-12-12 | Asset Listing | All Asset | Restrict the user to enter invalid value (instead of Confirm) , this applies to the fields including detail search and add page |  | Shalini | Nachiappan | Open | High | john | Dec 16 As per dis with Priya we have increased digits up to 5. In future we will restric the user in typing more than 5 decimal digit 18Dec - Priya - Dont see this changes in QA link
222 | 2021-12-12 | Asset Listing | All Asset | Remove 'Select Asset Type' from structure code field |  | Priya |  | Closed
223 | 2021-12-12 | Asset Listing | Guardrail | Add>ID -Asset Group and Asset Type are missing in ID generation(eg://MRI/1/Q292/1+222/R) |  | Shalini | Vasanth | Closed
224 | 2021-12-12 | Asset Listing | Guardrail | Add >Photo>No Values in Photo type dropdown |  | Shalini | Vasanth | Closed
225 | 2021-12-12 | Asset Listing | Guardrail | Menu>Asset Listing>Rename as Guard Rail to Guardrail |  | Shalini | tested by nisha | Closed
226 | 2021-12-12 | Asset Listing | Guardrail | Rename column in the grid postspacing to Guardrail post spacing |  | Shalini | Vasanth | Closed
227 | 2021-12-12 | Asset Listing | All Asset | Delete icon is removed in the view mode which is correct but it shows some unwanted space there instead the icon , have the icon and disable it else correct the space |  | Priya | designer | open | High
228 | 2021-12-12 | Asset Listing | All Asset | In View Photo - image view - should be in expand mode |  | Priya | Vasanth | Closed | Medium
229 | 2021-12-12 | Asset Listing | All Assets | Image View section - when we add new images it is getting displayed but the old ones are shows "image available" |  | Priya | kalai | Closed | High | Image tested locally may not be committed hence it is unavailable
230 | 2021-12-12 | Asset Listing | Carriageway | Lane Number should be a dropdown |  | Priya | kalai | Closed
231 | 2021-12-13 | Asset Listing | Global | Network issue needs to be handled , ex ( tried attaching same image 3 tines at the time of network failure , got "Object, Object" error from the system , tried uploading images again once netwrok back , previously uploaded photos along with recent got added) |  | Priya |  | open | Medium | This is negative case. will look later
232 | 14Dec | Asset Listing | Culvert | Detail search combination not working in(RMU -BATU NIAH and Bound-Left) (Id-CV/Culvert Pipe/BTN/5/Q647/0+0/Left) |  | Shalini | Pravin | Closed | High | Data that has been searched is of old one i.e created bound in the form of Left now replaced as L so data will not be filtered as expected.
233 | 14Dec | Asset Listing | Culvert | Detail search combination not working in(Section code-BATU NIAH and Bound-Left) (Id-CV/Culvert Pipe/BTN/5/Q647/0+0/Left) |  | Shalini | Pravin | Closed | High
234 | 14Dec | Asset Listing | All Asset | Sorting functionality is not working in Grid |  | Priya |  | open | Sorting
235 | 14Dec | Asset Listing | All Asset | Add-Choose one Road Feature Id(Respective fields get autofilled) then Unselect the Road Feature Id(autofilled values need to be remove) |  | Shalini | Vasanth | Closed | High
236 | 14Dec | Asset Listing | Except Culvert and Bridge (Remaining all) | Add-While opening the Add property page the Parameter Section is in Expanded format |  | Shalini | Vasanth | Closed | High
237 | 14Dec | Asset Listing | All Asset | Suggestion -Generate the ID instead of Choosing(Road feature id ,Asset type,Location CH and Bound),Better we gerenate it after user click the Confirm button |  | Shalini | Shriram | open | Low | Suggestion. Dec 23 : kalai Need clarification from shriram how this item is going to be handled globally in all forms
238 | 15Dec | Asset Listing | Road Stud | Asset CH column is missing in Grid |  | Shalini | kalai | Closed | High
239 | 15Dec | Asset Listing | Ditch | Rename Ditches into Ditch |  | Shalini | Nisha | Closed
240 | 15Dec | Asset Listing | Guardrail | Smart search not populating data in grid based on Guardrail Post Spacing (m) (ex 20.9) |  | Roopak | Pravin | Closed | High
241 | 15Dec | Asset Listing | Guardrail | In 'Add Guardrail' page under 'Parameter' section, 'Dimension(m)' field should split and change to "Length" and "Width" fields |  | Roopak |  | Closed |  | 16Dec-Priya - This is the design change
242 | 17Dec | Asset Listing |  | Need to change Asset Listing as Road Furniture in Breadcrumbs |  | Priya | Vasanth | Closed |  | 16Dec - Priya - UEM feedback
243 | 17Dec | Asset Listing |  | KM+M , should be changed to KM.M - alll places |  | Priya | Vasanth | Closed |  | 16Dec - Priya - UEM feedback
244 | 17Dec | Asset Listing |  | Without images - image path should not come in the download |  | Priya |  | Closed |  | 22Dec - Tracked in Asset Import/Download sheet S.No 6
246 | 17Dec | Asset Listing | All Asset | Cant able to view the image for jpeg format(it will shows the default image doc) |  | Shalini | Vasanth | Closed
247 | 17Dec | Asset Listing | All Asset | System should not accept the file size more than 5mb on image and 25 mb for others , should throw an validation message |  | Shalini | Vasanth/kalai | closed |  | 22Dec - Priya - Document max size should be 25 MB QA : User upload 5.02 mb files in Carriage way category at the time validation(The maximum file size for uploads should not exceed 5 MB) is appeared. Again user try to upload the same files at the time same error should be appeared but currently nothing happen
248 | 17Dec | Asset Listing | Sign | Sign asset when there is duplication , getting error msg twice on entering data in asset number |  | Priya | Vasanth | Closed |  | 22Dec - Priya - Getting error messge twice on adding data and removing data in 'Asset Number'
249 | 17Dec | Asset Listing | All Asset | System should not allow to upload files other than JPG and PNG in image type |  | Priya | Vasanth | Closed
250 | 18Dec | Asset Listing | All Asset | Text fields of type varchar shoould not accept more than 1000 characters Note : should not be applied to autofill fields |  | Priya |  | Closed
251 | 18Dec | Asset Listing | All Asset | Detail Search - Getting ajax error on trying data other than numbers in location fields |  | Priya | Vasanth | Closed
252 | 18Dec | Asset Listing | All Asset | Action column in the grid should be freezed |  | Priya |  | Closed
253 | 18Dec | Asset Listing | All Asset | Detail Search - Getting ajax error on closing Action(Edit,View,Delete) screen when performing detail search with the combination of location fields Note: Grid is not getting refreshed after deleting the record | Login - Road Furniture - All Asset - Detail Search - Enter valid data in Location CH(From and To) - Search - Click me - Open(Edit, View, Delete) - Close | Roopak | Vasanth | Closed
254 | 18Dec | Asset Listing | All Asset | Add & Edit Page - Location CH field is getiing enabled on clicking confirm | Login - Road Furniture - All Asset - Add/Edit - Enter invalid format in any field - Confirm (Ex: CH From- a or @) | Roopak | Nisha | Closed
255 | 18Dec | Asset Listing | All Asset | Culvert D - represents Diameter or Depth (is it user friendly) |  |  | Shriram | fixed |  | 18Dec - Need to discuss with Shriram Shriram: I would prefer haveing the full descripton. owever, as these sreens are currently in UAT - if UEM feels these are ok, then we should be fine.
256 | 18Dec | Asset Listing | All Asset | Do we need Road Name column in the grid for all the asset to have consistency as per the requirement its there for few asset |  |  | Shriram | fixed |  | 19Dec - Need to discuss with Shriram Shriram - I would also prefer having Road Code and Road Name listed. As these screens are in UAT, if they are ok then we should be fine.
257 | 2021-12-19 | Asset Listing | All Asset | Other Category - only PDF, docx, doc, xlsx, csv, xls,PNG, JPG,JPEG is allowed except |  | Priya | vasanth | Closed
258 | 2021-12-19 | Asset Listing | Ditch | Change Add Ditches to Add Ditch Change Ditches to Ditch in landing page Change Ditches Property to Ditch Property Change Ditches to Ditch in Breadcrumb |  | Priya | Prabhu/Nisha | Closed
259 | 21Dec | Asset Listing | All Asset | Unable to navigate to the file attached in other category on clicking View Photo |  | Priya | Nisha | Closed
260 | 2021-12-19 | Asset Listing | Guardail | Guardrail->cant able to see the uploaded image in view photo(In QA Link) |  | Shalini | Tested by nisha | Closed
261 | 21Dec | Asset Listing | All Asset | Jfif - able to upload this file in image category without any error |  | Priya | Nisha | closed |  |  | While downloading Jfif file, it saved in png format. So only it can upload w/o any error. 21Dec - I uploaded a Jfif file directly without saving as PNG 22Dec - Priya - I am updating the status from Need to discuss to Open as discussed the issue with Nisha
262 | 21Dec | Asset Listing | All Asset | Error Location Chainage TO cannot be less then From - appears even the values are passed correctly |  | Priya | Kalai | Closed
263 | 22Dec | Asset Listing | All Asset | Add Page - Location CH(KM and M) field is getting disabled on confirm with invalid/No data entered in the field and 'Structure Code' is not displaying value according to 'Asset Type' selected and 'District' and 'Reference No' is getting disabled | 1. Click any Add Asset Page 2. Select Road Feature ID 3. Click Confirm | Priya | Nisha | Closed
264 | 22Dec | Asset Listing | All Asset | Edit Page - 'District' and 'Reference No' is getting disabled, on confirm with invalid data entered in one of the field | 1. Click any Edit Asset Page 2. Enter invalid data in any field 3. Click Confirm | Priya | Nisha | closed
265 | 22Dec | Asset Listing | All Asset | In grid, 'Bound' code missing and '//' is showing in 'Asset ID' | 1. Click any Add Asset Page 2. Select Road Feature ID 3. Enter valid data in Location CH 4. Click Confirm 5. Select Asset Type and Bound->Confirm | Priya |  | Closed
266 | 23Dec | Asset Listing | All Asset | Operations (ERT)-Able to view the record (But this user group has no permission to view the module) -eg.michelle.huang | User Permission | Shalini | kalai | Not an issue
267 | 23Dec | Asset Listing | All Asset | Need Username for this Group(Operations (Region Manager), | User Permission | Shalini | prabhu | Reopen
268 | 25Dec | Asset Listing | Bridge | Detail Search-Give incorrect multiple data in Location CH fields (eg:abc@$@$)It will shows multiple times of error message. | Bridge | Shalini |  | Open
269 | 25Dec | Asset Listing | Bridge | System should not allow user to save the record without Asset Type and Bound | Bridge | Shalini |  | Open
270 | 25Dec | Asset Listing | All Asset | Add-Give incorrect data in Location CH Field-Click Confirm(It will show error message but cant able to edit the value) |  | Shalini |  | Open | High
271 | 25Dec | Asset Listing | Bridge | Give incorrect data in Built year(In error message change year into Built year) | Bridge-Add Bridge | Shalini |  | Open
272 | 25Dec | Asset Listing | Bridge | Enter Incorrect data type (Eg;Lane width-abc)It will show the error message behind of the modal | Bridge-Add Bridge | Shalini |  | Closed
273 | 2021-12-29 | All Assets | Sorting | Sorting ID is not working properly ascending order and descending order functionality is not working properly | All Main grid | Shalini |  | open | Sorting
274 | 2021-12-29 | All Assets | Sorting | Road Code ascending order and descending order functionality is not working properly | All Main grid | Shalini |  | open | Sorting
275 | 2021-12-29 | All Assets | Sorting | Location CH ascending order and descending order functionality is not working properly | All Main grid | Shalini |  | open | Sorting
276 | 2021-12-29 | All Assets | Sorting | CH From, CH To, Asset Type, Bounded - Need to implement sorting functionality | All Main grid | Shalini |  | open | Sorting